## Posting Label
Posting Label
manifestAPI | workstream.initiatives.a6i.io/v1a
workstreamUID | W1
workstreamTitle | Modernization
program | Amplify
initiative | S1
scenario | Default
data.kind.1 | workstream-milestone
data.range.1 | B2:I100
data.sheet.1 | Milestones
data.kind.2 | workstream-metric
data.range.2 | B2:O100
data.sheet.2 | Metrics
organization | My Corp
environment | Production
scoringCycle | Dec 2020
scoringMaturity | Draft
estimatedBy | joe.theworkstreamlead@mycorp.com
estimatedOn | 2021-04-29
recordedBy | jill.theinitiativepmo@mycorp.com

## Milestones
Milestones
UID | Theme | Milestone | Date due | Task | Task Date | Dependency | Dependent on
| Commercial alignment | Align roadmaps to MTP bookings projection | 2021-07-31 | Break up journey into "big rocks" mapped to "milestones" | 2021-06-15
|  |  |  | Engage GMs and Finance to see roadmap expectations behind booking projections | 2021-07-15
|  |  |  | Update roadmap and/or MTP booking projections | 2021-07-31
| Product strategy alignment | Align to value props emerging from W0 | 2021-09-30 |  |  | Completion of W0 initial analysis (expected by end of August) | W0
| Incorporation of GTM requirements | Reflect GTM requirements in roadmaps | 2021-11-30 |  |  | Receipt of requirements from sales, pricing and support (expected by end of August) | W5, W6, W8
|  | Delivery of GTM requirements for 30% of modernizing products | 2022-05-31
|  | Delivery of GTM requirements for 60% of modernizing products | 2023-05-31
|  | Delivery of GTM requirements for 100% of modernizing products | 2024-05-31
| Adoption of FusionOperate | Baseline FusionOperate adoption targets | 2022-08-31 | Agree plan with the EAs | 2021-07-31
|  |  |  | Convey plan to FO Team | 2021-08-31
|  | Delivery of Fusion Operate aggregate adoption targets (gorwth product target and new product target) for FY 22 | 2022-05-31 |  |  | Availability of FusionOperate for pertinent stacks by 11/30/21 | W2
|  | Delivery of Fusion Operate aggregate adoption targets (gorwth product target and new product target) for FY 23 | 2023-05-31 |  |  | Availability of FusionOperate for pertinent stacks by 8/31/22 | W2
|  | Delivery of Fusion Operate aggregate adoption targets (gorwth product target and new product target) for FY 24 | 2024-05-31 |  |  | Availability of FusionOperate for pertinent stacks by 8/31/23 | W2

## Metrics
Metrics
UID | Metric | Metric Type | Granularity | Definition of metric | Baseline Value | Q1 FY 22 Target | Q2 FY22 Target | Q3 FY22 Target | Q4 FY 22 Target | FY 23 Target | FY 24 Target | Source | Frequency of Collection
M1 | FusionOperate readiness | R | ELT | Aggregation across all products of the product-specific metric M4 | TBD 8/31/21 |  |  |  | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | ea-journeys knowledge base system | Annual
M2 | Containerization, PaaS, Multi-tenancy | P | ELT | Aggregation across all products of the product-specific metrics M6, M7, M8 | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | ea-journeys knowledge base system | Quarterly
M3 | Aggregated # of epics delivered | P | ELT | Aggregation across all products of the product-specific metric M9 |  | 100% | 100% | 100% | 100% | 100% | 100% | Aha and the the ea-journeys knowledge base system. | Quarterly
M4 | Roadmap delivery (growth products) | R | Growth products | Metric computed from the 7 FusionOperate adoption indicators that exist for each growth product that is stacked ranked above a threshold (~8 products). Of the 7 indicators, 3 are for W1 and 4 are for W2. Computation procedure is: 1. For a given fiscal year, we sum up the numerical targets across 3 W1 FO indicators * ~8 growth products (~24 numbers added). This is the denominator 2. For the same fiscal year, we measure what the actuals are for these indicators, and add them up (~24 numbers added). This is the numerator 3. Metric is defined as the ratio, defined as a percent. | TBD 8/31/21 |  |  |  | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | ea-journeys knowledge base system | Annual
M5 | Roadmap delivery (new products) | R | New products | Same as above, for for new products instead of growth products. | TBD 8/31/21 |  |  |  | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | ea-journeys knowledge base system | Annual
M6 | Margin enablement | P | Growth products | Same as for roadmap delivery, except the sum is only over 1 FO Adoption indicator (the "% containerized" indicator) | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | ea-journeys knowledge base system | Quarterly
M7 | Maintainability enablement | P | Growth products | Same as for roadmap delivery, except the sum is only over 1 FO Adoption indicator (the "% PaaS" indicator) | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | ea-journeys knowledge base system | Quarterly
M8 | Scalability enablement | P | Growth products | Same as for roadmap delivery, except the sum is only over 1 FO Adoption indicator (the "% multi-tenant" indicator) | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | ea-journeys knowledge base system | Quarterly
M9 | # of EPICs delivered in time and budget | P | Per growth product | Metric is separately reported for each of 14 growth products and computed as follows: 1. Product modernization roadmaps will be defined based on milestones that align to Amplify booking projections. 2. A given milestone M will map to some Aha epics E1, E2,, En defining the scope of M. 3. Each epic Ei has particular delivery date Ti. 4. For a given quarter Q, we define the metric by looking at the subset E_Q of {E1, ...., En} that were initially committed for delivery in Q. Metric is the % of E_Q that was actualy delivered in quarter Q. | N/A | 100% | 100% | 100% | 100% | 100% | 100% | Aha and the the ea-journeys knowledge base system. | Quarterly