## Sheet1
Posting Label | [7 empty] | Milestones
manifestAPI | milestone.journeys.a6i.io/v1 | [6 empty] | Milestone | M1 | M2 | M3 | M4
product | Opus Health Pro | [6 empty] | Theme | Complete MVP for medium-sized hospital market | Complete digital records for patients | Saas Solution for US | SaaS solution for Latin America
journey | Modernization | [6 empty] | Date | Q3 FY22 | Q2 FY 23 | Q4 FY 24 | Q4 FY 25
scenario | Annual plan
data.kind.1 | Modernization milestone
data.range.1 | L2:P30 | UID | Big Rock | UID | Breakdown | UID | Sub Breakdown |  | M1 | M2 | M3 | M4
data.kind.2 | Big rock | BR1 | Cloud Operating Model | 1.1 | Haas - Model hospital |  |  |  | x
data.range.2 | E7:J50 |  |  | 1.2 | Haas - Support & Maintenance |  |  |  | x
organization | CCL |  |  | 1.3 | Continuous Improvement | 1.3.1 | MVP 1 |  |  | x
environment | Production |  |  |  |  | 1.3.2 | MVP 2 |  |  |  | x
scoringCycle | FY 22 |  |  |  |  | 1.3.3 | MVP 3 |  |  |  |  | x
scoringMaturity | Draft | BR2 | Tech Roadmap | 2.1 | Patient Unit Test Framework |  |  |  | x
estimatedBy | joe@my-org.com |  |  | 2.2 | Health regulator and Technical stack certification |  |  |  | x
estimatedOn | 2021-06-06 |  |  | 2.3 | HIPAA Performance Improvement |  |  |  | x
recordedBy | tulia@my-org.com |  |  | 2.4 | Technology Improvements | 2.4.1 | Simiplify Core - Java 8 build/runtime adoption |  |  | x
[6 empty] | 2.4.2 | Crystal Report Replacement |  |  |  | x
[6 empty] | 2.4.3 | Automatic recovery of asynchronous framework tasks |  | x
[6 empty] | 2.4.4 | Improve data grid component - SLA dashboard |  |  |  | x
[6 empty] | 2.4.5 | Archiving Tools |  |  |  | x
[6 empty] | 2.4.6 | License audit tool enhancement |  |  |  |  | x
[6 empty] | 2.4.7 | Other Continuous Tech roadmap items (tbc) |  |  |  |  | x
|  | BR3 | Healthcare Ecosystem - Open API | 3.1 | Connectivity with WHO |  |  |  | x
|  |  |  | 3.2 | Integration with CDC |  |  |  | x
|  |  |  | 3.3 | Digital Clinic Ecosystem | 3.3.1 | Consalut Guarantees |  | x
[6 empty] | 3.3.2 | *New use cases - TBC later (e.g. Contour/Komgo, Tradeteq, Data API) |  |  | x
[6 empty] | 3.3.3 | *New use cases - TBC later (e.g. Contour/Komgo, Tradeteq, Data API) |  |  |  | x
[6 empty] | 3.3.4 | *New use cases - TBC later (e.g. Contour/Komgo, Tradeteq, Data API) |  |  |  |  | x